## Focused GAs -MOPNG DATA (hidden)
Natio+A1:Q11nal PNG Drive 2.0 Targets - Focus GAs (110) | [6 empty] | Cummulative |  |  |  | PNG Drive before 16th March |  |  |  | 16th March 2026 |  |  |  | 17th March 2026 |  |  |  | 18th March 2026 |  |  |  | 19th March 2026 |  |  |  | 20th March 2026 |  |  |  | 21st March 2026 |  |  |  | 22nd March 2026 |  |  |  | 23rd March 2026 |  |  |  | 24th March 2026 |  |  |  | 25th March 2026 |  |  |  | 26th March 2026 |  |  |  | 27th March 2026 |  |  |  | 28th March 2026 |  |  |  | 30th March 2026 |  |  |  | 31st March 2026 |  |  |  | 1st April 2026 |  |  |  | 2nd April 2026 |  |  |  | 3rd April 2026 |  |  |  | Total 16th Mar-Till Date
S No | GA ID | GA Name | DPNG Target (Drive) |  |  | Commercial Connections | Cumm. DPNG |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in) | DPNG Progress |  |  | Commercial Connections Completed (Gas-in)
|  |  | Connections | Connected to Billed | Registrations |  | LMC | NGC | Registrations |  | LMC | NGC | Registrations |  | New Connections | Connected to Billed | Registrations |  | New Connections | Connected to Billed | Registrations |  | New Connections | Connected to Billed | Registrations |  | New Connections | Connected to Billed | Registrations |  | New Connections | Connected to Billed | Registrations |  | New Connections | Connected (Old RFC) to Billed | Registrations |  | New Connections | Connected (Old RFC) to Billed | Registrations |  | New Connections | Connected (Old RFC) to Billed | Registrations |  | New Connections | Connected (Old RFC) to Billed | Registrations |  | New Connections | Connected (Old RFC) to Billed | Registrations |  | New Connections | Connected (Old RFC) to Billed | Registrations |  | New Connections | Connected (Old RFC) to Billed | Registrations |  | New Connections | Connected (Old RFC) to Billed | Registrations |  | New Connections | Connected (Old RFC) to Billed | Registrations |  | New Connections | Connected (Old RFC) to Billed | Registrations |  | New Connections | Connected (Old RFC) to Billed | Registrations |  | New Connections | Connected (Old RFC) to Billed | Registrations |  | New Connections | Connected (Old RFC) to Billed | Registrations |  | New Connections | Connected (Old RFC) to Billed | Registrations
1 | 10.37 | Bareilly (EAAA) District, Pilibhit and Rampur Districts | 15000 | 20000 | 30000 | 5 | 1068 | 1068 | 28185 | 0 | 1331 | 1133 | 626 |  | 9 | 13 | 0 | 0 | 3 | 6 | 3 | 0 | 4 | 14 | 9 | 0 | 4 | 17 | 13 | 0 | 4 | 17 | 13 | 0 | 0 | 10 | 13 | 0 | 0 | 5 | 0 | 0 | 4 | 8 | 5 | 0 | 0 | 9 | 3 | 0 | 0 | 15 | 3 | 0 | 0 | 15 | 3 | 0 | 20 | 14 | 5 | 0 | 7 | 14 | 3 | 0 | 12 | 18 | 3 | 0 | 10 | 16 | 10 | 0 | 7 | 17 | 10 | 0 | 8 | 20 | 5 | 0 | 7 | 14 | 5 | 0 | 84 | 208 | 96 | 0
2 | 10.47 | Darjeeling, Jalpaiguri and Uttar Dinajpur Districts | 15000 | 20000 | 30000 | 20 | 12248 | 501 | 17611 | 1 | 5068 | 531 | 2514 |  | 0 | 223 | 35 | 0 | 76 | 40 | 123 | 0 | 50 | 20 | 38 | 0 | 94 | 10 | 98 | 0 | 94 | 10 | 98 | 0 | 71 | 0 | 3 | 1 | 62 | 5 | 2 | 0 | 4 | 5 | 5 | 1 | 115 | 7 | 5 | 0 | 3 | 8 | 4 | 0 | 68 | 15 | 17 | 0 | 61 | 18 | 9 | 0 | 35 | 20 | 25 | 0 | 33 | 23 | 37 | 0 | 71 | 30 | 35 | 0 | 21 | 30 | 34 | 1 | 23 | 20 | 30 | 0 | 85 | 28 | 5 | 0 | 858 | 464 | 568 | 3
3 | 10.39 | Farrukhabad, Etah and Hardoi Districts | 15000 | 25000 | 30000 | 20 | 18744 | 940 | 30271 | 0 | 1530 | 617 | 495 |  | 5 | 5 | 9 | 0 | 1 | 1 | 0 | 0 | 5 | 3 | 3 | 0 | 16 | 24 | 8 | 0 | 16 | 24 | 8 | 0 | 5 | 14 | 9 | 0 | 4 | 3 | 11 | 0 | 2 | 2 | 20 | 0 | 5 | 3 | 10 | 0 | 6 | 4 | 9 | 0 | 25 | 15 | 12 | 0 | 30 | 10 | 21 | 0 | 30 | 10 | 10 | 0 | 27 | 10 | 12 | 0 | 36 | 15 | 14 | 0 | 18 | 10 | 14 | 0 | 43 | 10 | 22 | 0 | 16 | 5 | 15 | 0 | 231 | 153 | 170 | 0
4 | 10.48 | Howrah (EAAA) District and Hoogly (EAAA) District | 20000 | 20000 | 40000 | 20 | 8768 | 125 | 14449 | 0 | 2207 | 194 | 1455 |  | 140 | 0 | 45 | 0 | 39 | 0 | 43 | 0 | 4 | 4 | 39 | 0 | 1 | 10 | 46 | 0 | 1 | 10 | 46 | 0 | 14 | 10 | 12 | 0 | 17 | 2 | 22 | 0 | 2 | 2 | 32 | 1 | 70 | 6 | 35 | 0 | 35 | 6 | 25 | 0 | 27 | 3 | 25 | 0 | 20 | 8 | 17 | 0 | 15 | 6 | 25 | 1 | 12 | 6 | 17 | 0 | 22 | 5 | 17 | 0 | 2 | 5 | 16 | 0 | 21 | 4 | 27 | 0 | 19 | 4 | 25 | 0 | 421 | 83 | 462 | 2
5 | 10.49 | Nadia (EAAA) District and North 24 Parganas (EAAA) District | 15000 | 15000 | 30000 | 10 | 15942 | 349 | 19739 | 0 | 4892 | 495 | 1552 |  | 27 | 19 | 38 | 0 | 12 | 14 | 10 | 0 | 9 | 0 | 18 | 0 | 80 | 0 | 55 | 0 | 80 | 0 | 55 | 0 | 56 | 8 | 17 | 0 | 10 | 0 | 8 | 0 | 1 | 1 | 1 | 1 | 80 | 1 | 8 | 0 | 20 | 2 | 9 | 0 | 81 | 5 | 15 | 0 | 39 | 3 | 33 | 0 | 40 | 5 | 8 | 1 | 49 | 7 | 11 | 6 | 42 | 6 | 12 | 0 | 20 | 11 | 30 | 0 | 78 | 14 | 20 | 0 | 10 | 15 | 7 | 0 | 646 | 82 | 328 | 8
6 | 10.45 | Shahjahanpur and Budaun Districts | 15000 | 20000 | 30000 | 5 | 19639 | 2884 | 39248 | 4 | 1449 | 453 | 595 |  | 19 | 19 | 1 | 0 | 18 | 16 | 0 | 0 | 16 | 12 | 0 | 0 | 32 | 26 | 0 | 0 | 32 | 26 | 0 | 0 | 0 | 12 | 13 | 0 | 0 | 7 | 0 | 0 | 0 | 2 | 0 | 0 | 5 | 6 | 2 | 0 | 40 | 12 | 2 | 0 | 40 | 12 | 2 | 0 | 0 | 13 | 11 | 0 | 94 | 18 | 0 | 0 | 10 | 35 | 0 | 0 | 53 | 27 | 1 | 0 | 49 | 41 | 99 | 0 | 16 | 7 | 0 | 0 | 42 | 7 | 0 | 0 | 408 | 284 | 131 | 0
7 | 9.19 | Sonipat District (EAAA) & Jind District | 15000 | 12000 | 30000 | 5 | 14983 | 4198 | 26569 | 2 | 97 | 426 | 18 |  | 5 | 22 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 4 | 1 | 0 | 7 | 11 | 10 | 0 | 7 | 11 | 10 | 0 | 0 | 6 | 0 | 1 | 1 | 8 | 0 | 0 | 0 | 3 | 0 | 4 | 7 | 3 | 4 | 1 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 2 | 5 | 10 | 2 | 2 | 7 | 5 | 1 | 0 | 2 | 11 | 2 | 0 | 0 | 49 | 6 | 3 | 0 | 10 | 4 | 0 | 2 | 10 | 0 | 0 | 54 | 157 | 37 | 13
|  | Total | 110000 | 132000 | 220000 | 85 | 91392 | 10065 | 176072 | 7 | 16574 | 3849 | 7255 |  | 205 | 301 | 128 | 0 | 149 | 78 | 180 | 0 | 89 | 57 | 108 | 0 | 234 | 98 | 230 | 0 | 234 | 98 | 230 | 0 | 146 | 60 | 67 | 2 | 94 | 30 | 43 | 0 | 13 | 23 | 63 | 7 | 282 | 35 | 67 | 1 | 108 | 51 | 52 | 0 | 245 | 69 | 74 | 0 | 174 | 71 | 96 | 2 | 226 | 83 | 73 | 4 | 150 | 104 | 81 | 6 | 236 | 110 | 91 | 0 | 117 | 163 | 209 | 4 | 189 | 85 | 108 | 0 | 181 | 83 | 57 | 0 | 2702 | 1431 | 1792 | 26
Cumm for CGD | [6 empty] | 1,57,435 | 12266 | 2,58,070 | 53 (com+ind)
10829

## All GAs (hidden)
GA ID | GA Area | State/UTs | Target PNGRB |  |  |  | PNG Progress - 1st Jan- 22nd Mar'26 |  |  |  | PNG Progress 23rd Mar'26 |  |  |  | PNG Progress 24th Mar'26 |  |  |  | PNG Progress 25th Mar'26 |  |  |  | PNG Progress 26th Mar'26 |  |  |  | PNG Progress 27th Mar'26 |  |  |  | PNG Progress 28th Mar'26 |  |  |  | PNG Progress 29th Mar'26 |  |  |  | PNG Progress 30th Mar'26 |  |  |  | PNG Progress 31st Mar'26 |  |  |  | PNG Progress 1st April'26 |  |  |  | PNG Progress 2nd April'26 |  |  |  | PNG Progress 3rd April'26 |  |  |  | PNG Progress Cumm.
|  |  | LMC | NGC | Registartion | Comm/Ind. | LMC | NGC | Registartion | Comm/Ind. | LMC | NGC | Registartion | Comm/Ind. | LMC | NGC | Registartion | Comm/Ind. | LMC | NGC | Registartion | Comm/Ind. | LMC | NGC | Registartion | Comm/Ind. | LMC | NGC | Registartion | Comm/Ind. | LMC | NGC | Registartion | Comm/Ind. | LMC | NGC | Registartion | Comm/Ind. | LMC | NGC | Registartion | Comm/Ind. | LMC | NGC | Registartion | Comm/Ind. | LMC | NGC | Registartion | Comm/Ind. | LMC | NGC | Registartion | Comm/Ind. | LMC | NGC | Registartion | Comm/Ind. | LMC | NGC | Registartion | Comm/Ind.
|  |  | Nos | Nos. | Nos. | Enrollment | Nos | Nos. | Nos. | Enrollment | Nos | Nos. | Nos. | Enrollment | Nos | Nos. | Nos. | Enrollment | Nos | Nos. | Nos. | Enrollment | Nos | Nos. | Nos. | Enrollment | Nos | Nos. | Nos. | Enrollment | Nos | Nos. | Nos. | Enrollment | Nos | Nos. | Nos. | Enrollment | Nos | Nos. | Nos. | Enrollment | Nos | Nos. | Nos. | Enrollment | Nos | Nos. | Nos. | Enrollment | Nos | Nos. | Nos. | Enrollment | Nos | Nos. | Nos. | Enrollment | Nos | Nos. | Nos. | Enrollment
10.37 | Bareilly, Rampur, Pilibhit | UP | 15000 | 20000 | 30000 | 5 | 894 | 418 | 650 | 0 | 4 | 8 | 5 | 0 | 0 | 9 | 3 | 0 | 0 | 15 | 3 | 0 | 0 | 15 | 3 | 0 | 20 | 14 | 5 | 0 | 7 | 14 | 3 | 0 | 12 | 18 | 3 | 0 | 10 | 18 | 5 | 0 | 10 | 16 | 10 | 0 | 7 | 17 | 10 | 0 | 8 | 20 | 5 | 0 | 7 | 14 | 5 | 0 | 66 | 131 | 49 | 0
10.47 | Darjeeling, Jalpaiguri & Uttar Dinajpur | WB | 15000 | 20000 | 30000 | 20 | 3142 | 571 | 2731 | 1 | 4 | 5 | 5 | 1 | 115 | 7 | 5 | 0 | 3 | 8 | 4 | 0 | 68 | 15 | 17 | 0 | 61 | 18 | 9 | 0 | 35 | 20 | 25 | 0 | 33 | 23 | 37 | 0 | 43 | 18 | 41 | 0 | 71 | 30 | 35 | 0 | 21 | 30 | 34 | 1 | 23 | 20 | 30 | 0 | 85 | 28 | 5 | 0 | 441 | 163 | 201 | 2
10.39 | Etah, Farrukhabad, Hardoi | UP | 15000 | 25000 | 30000 | 20 | 630 | 134 | 515 | 0 | 2 | 2 | 20 | 0 | 5 | 3 | 10 | 0 | 6 | 4 | 9 | 0 | 25 | 15 | 12 | 0 | 30 | 10 | 21 | 0 | 30 | 10 | 10 | 0 | 27 | 10 | 12 | 0 | 9 | 4 | 15 | 0 | 36 | 15 | 14 | 0 | 18 | 10 | 14 | 0 | 43 | 10 | 22 | 0 | 16 | 5 | 15 | 0 | 198 | 79 | 138 | 0
10.48 | Howrah & Hooghly | WB | 20000 | 20000 | 40000 | 20 | 1662 | 98 | 1519 | 1 | 2 | 2 | 32 | 0 | 70 | 6 | 35 | 0 | 35 | 6 | 25 | 0 | 27 | 3 | 25 | 0 | 20 | 8 | 17 | 0 | 15 | 6 | 25 | 1 | 12 | 6 | 17 | 0 | 13 | 5 | 12 | 0 | 22 | 5 | 17 | 0 | 2 | 5 | 16 | 0 | 21 | 4 | 27 | 0 | 19 | 4 | 25 | 0 | 192 | 44 | 206 | 1
10.49 | Nadia & North 24 Parganas | WB | 15000 | 15000 | 30000 | 10 | 4209 | 149 | 1455 | 0 | 1 | 1 | 1 | 1 | 80 | 1 | 8 | 0 | 20 | 2 | 9 | 0 | 81 | 5 | 15 | 0 | 39 | 3 | 33 | 0 | 40 | 5 | 8 | 1 | 49 | 7 | 11 | 6 | 36 | 6 | 9 | 0 | 42 | 6 | 12 | 0 | 20 | 11 | 30 | 0 | 78 | 14 | 20 | 0 | 10 | 15 | 7 | 0 | 417 | 52 | 136 | 2
10.45 | Shahjahanpur Badaun | UP | 15000 | 20000 | 30000 | 5 | 775 | 372 | 621 | 0 | 0 | 2 | 0 | 0 | 5 | 6 | 2 | 0 | 40 | 12 | 2 | 0 | 40 | 12 | 2 | 0 | 0 | 13 | 11 | 0 | 94 | 18 | 0 | 0 | 10 | 35 | 0 | 0 | 53 | 27 | 1 | 0 | 53 | 27 | 1 | 0 | 49 | 41 | 99 | 0 | 16 | 7 | 0 | 0 | 42 | 7 | 0 | 0 | 310 | 153 | 116 | 0
9.19 | Sonipat - Jind GA | Haryana | 15000 | 12000 | 30000 | 5 | 120 | 235 | 55 | 3 | 0 | 3 | 0 | 2 | 7 | 3 | 4 | 1 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 5 | 0 | 2 | 5 | 10 | 2 | 2 | 7 | 5 | 1 | 0 | 4 | 6 | 0 | 0 | 2 | 11 | 2 | 0 | 0 | 49 | 6 | 3 | 0 | 10 | 4 | 0 | 2 | 10 | 0 | 0 | 26 | 101 | 18 | 10
10.43 | Mainpuri Kannauj | UP | 10000 | 5000 | 20000 | 8 | 960 | 423 | 665 | 1 | 9 | 8 | 8 | 0 | 10 | 13 | 10 | 0 | 10 | 20 | 4 | 0 | 10 | 20 | 4 | 0 | 8 | 20 | 4 | 0 | 10 | 14 | 3 | 0 | 10 | 20 | 6 | 0 | 10 | 18 | 8 | 0 | 10 | 30 | 5 | 0 | 8 | 32 | 6 | 0 | 6 | 15 | 2 | 0 | 7 | 9 | 6 | 0 | 81 | 170 | 50 | 0
10.46 | Nainital Bijnor | UK/UP | 10000 | 5000 | 20000 | 8 | 483 | 429 | 104 | 0 | 5 | 0 | 24 | 0 | 2 | 0 | 18 | 0 | 2 | 3 | 4 | 0 | 5 | 8 | 15 | 0 | 5 | 14 | 12 | 0 | 11 | 15 | 15 | 0 | 16 | 25 | 8 | 0 | 5 | 19 | 5 | 0 | 15 | 24 | 22 | 0 | 10 | 19 | 25 | 0 | 10 | 17 | 0 | 0 | 15 | 16 | 0 | 0 | 68 | 116 | 136 | 0
10.5 | South 24 Parganas | WB | 10000 | 5000 | 20000 | 8 | 700 | 28 | 438 | 0 | 7 | 1 | 5 | 0 | 8 | 0 | 2 | 0 | 6 | 0 | 8 | 0 | 6 | 0 | 8 | 0 | 2 | 0 | 5 | 0 | 2 | 3 | 1 | 0 | 2 | 2 | 9 | 0 | 1 | 9 | 1 | 0 | 2 | 2 | 10 | 0 | 2 | 2 | 9 | 0 | 4 | 0 | 2 | 0 | 7 | 1 | 10 | 0 | 34 | 17 | 43 | 0
11.44 | Dausa, Karauli, Sawai Madhopur & Tonk | RJ | 10000 | 5000 | 20000 | 5 | 1853 | 34 | 1933 | 0 | 24 | 2 | 22 | 0 | 22 | 3 | 20 | 0 | 10 | 5 | 12 | 0 | 20 | 2 | 18 | 0 | 18 | 4 | 19 | 0 | 22 | 5 | 16 | 0 | 19 | 8 | 17 | 0 | 10 | 6 | 12 | 0 | 19 | 7 | 17 | 0 | 17 | 11 | 19 | 0 | 20 | 6 | 12 | 0 | 19 | 6 | 18 | 0 | 172 | 46 | 155 | 0
11A.02 | Banka, Dumka, Godda. Jamtara, Pakur & Sahibganj | Bihar/Jharkhand | 10000 | 5000 | 20000 | 0 | 1069 | 0 | 1135 | 0 | 8 | 0 | 5 | 0 | 9 | 0 | 30 | 0 | 7 | 0 | 10 | 0 | 10 | 0 | 17 | 0 | 11 | 0 | 12 | 0 | 7 | 0 | 7 | 0 | 11 | 0 | 10 | 0 | 8 | 0 | 11 | 0 | 10 | 0 | 13 | 0 | 15 | 0 | 10 | 0 | 13 | 13 | 13 | 13 | 9 | 0 | 13 | 0 | 91 | 13 | 118 | 13
11A.03 | Birbhum, Mursiddabad, Maldah | WB | 10000 | 5000 | 20000 | 5 | 854 | 0 | 1877 | 0 | 20 | 0 | 13 | 0 | 20 | 0 | 13 | 0 | 15 | 0 | 12 | 0 | 21 | 0 | 15 | 0 | 21 | 0 | 20 | 0 | 12 | 0 | 13 | 0 | 16 | 0 | 21 | 0 | 20 | 0 | 14 | 0 | 27 | 0 | 25 | 0 | 29 | 0 | 31 | 0 | 22 | 0 | 26 | 0 | 25 | 0 | 23 | 0 | 192 | 0 | 170 | 0
12.05 | Sikkim | Sikkim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  | 170000 | 162000 | 340000 | 119 | 17351 | 2891 | 13698 | 6 | 86 | 34 | 140 | 4 | 353 | 51 | 160 | 1 | 158 | 79 | 102 | 0 | 317 | 99 | 151 | 0 | 239 | 109 | 168 | 2 | 290 | 120 | 128 | 4 | 224 | 159 | 152 | 6 | 222 | 136 | 134 | 0 | 319 | 173 | 183 | 0 | 198 | 227 | 309 | 4 | 264 | 136 | 163 | 13 | 263 | 115 | 127 | 0 | 2288 | 1085 | 1536 | 28
16555
[60 empty] | 10829 | 3406 | 2349

## MIS Summary
Summary | Cum. MARCH-26 |  | 1st April |  | 2nd April |  | 3rd April |  | 4th April |  | Cumulative April'26 |  | Cumulative NGC
Entity Name | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | Grand total NGC
HPCL | 2366 | 2022 | 154 | 227 | 229 | 123 | 229 | 115 | 189 | 104 | 801 | 569 | 3167 | 2591 | 5758
HOGPL | 84 | 475 | 12 | 18 | 1 | 36 | 0 | 27 | 2 | 74 | 15 | 155 | 99 | 630 | 729
BGL | 212 | 508 | 0 | 43 | 1 | 38 | 2 | 60 | 2 | 39 | 5 | 180 | 217 | 688 | 905
Total | 2662 | 3005 | 166 | 288 | 231 | 197 | 231 | 202 | 193 | 217 | 821 | 904 | 3483 | 3909 | 7392
Grand Total | 5667 |  | 454 |  | 428 |  | 433 |  | 410 |  | 1725 |  | 7392

## HPCL-JV MIS
NGC Progress MIS – Gasified Geographical Area (HPCL & JVs)
HPCL |  |  | Cum MARCH-26 |  | 1st April |  | 2nd April |  | 3rd April |  | 4th April |  | Cumulative April'26 |  | Cumulative NGC
GA ID | GA Area | State/UTs | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | Grand total NGC
10.37 | Bareilly, Rampur, Pilibhit | UP | 84 | 233 | 7 | 17 | 8 | 20 | 7 | 14 | 10 | 24 | 32 | 75 | 116 | 308 | 424
10.47 | Darjeeling, Jalpaiguri & Uttar Dinajpur | WB | 688 | 546 | 21 | 30 | 23 | 20 | 85 | 28 | 79 | 21 | 208 | 99 | 896 | 645 | 1541
10.39 | Etah, Farrukhabad, Hardoi | UP | 231 | 141 | 18 | 10 | 43 | 10 | 16 | 5 | 14 | 6 | 91 | 31 | 322 | 172 | 494
10.48 | Howrah & Hooghly | WB | 421 | 56 | 2 | 5 | 21 | 4 | 19 | 4 | 21 | 4 | 63 | 17 | 484 | 73 | 557
10.49 | Nadia & North 24 Parganas | WB | 400 | 137 | 20 | 11 | 78 | 14 | 10 | 15 | 4 | 10 | 112 | 50 | 512 | 187 | 699
10.45 | Shahjahanpur Badaun | UP | 408 | 296 | 49 | 41 | 16 | 7 | 42 | 7 | 25 | 7 | 132 | 62 | 540 | 358 | 898
9.19 | Sonipat - Jind GA | Haryana | 54 | 193 | 0 | 49 | 0 | 10 | 2 | 10 | 0 | 0 | 2 | 69 | 56 | 262 | 318
10.43 | Mainpuri Kannauj | UP | 20 | 232 | 8 | 32 | 6 | 15 | 7 | 9 | 6 | 9 | 27 | 65 | 47 | 297 | 344
10.46 | Nainital Bijnor | UK/UP | 5 | 167 | 10 | 19 | 10 | 17 | 15 | 16 | 8 | 15 | 43 | 67 | 48 | 234 | 282
10.5 | South 24 Parganas | WB | 3 | 21 | 2 | 2 | 4 | 0 | 7 | 1 | 5 | 0 | 18 | 3 | 21 | 24 | 45
11.44 | Dausa, Karauli, Sawai Madhopur & Tonk | RJ | 52 | 0 | 17 | 11 | 20 | 6 | 19 | 6 | 17 | 8 | 73 | 31 | 125 | 31 | 156
Total |  |  | 2366 | 2022 | 154 | 227 | 229 | 123 | 229 | 115 | 189 | 104 | 801 | 569 | 3167 | 2591 | 5758
Grand Total |  |  | 4388 |  | 381 |  | 352 |  | 344 |  | 293 |  | 1370 |  | 5758
HOGPL |  |  | Cum MARCH-26 |  | 1st April |  | 2nd April |  | 3rd April |  | 4th April |  | Cumulative April'26 |  | Cumulative NGC
GA ID | GA Area | State/UTs | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | Grand total NGC
8.03 | Ambala & Kurukshetra Districts | Haryana | 74 | 251 | 12 | 7 | 1 | 21 | 0 | 19 | 2 | 39 | 15 | 86 | 89 | 337 | 426
8.04 | Kolhapur District | Maharashtra | 10 | 224 | 0 | 11 | 0 | 15 | 0 | 8 | 0 | 35 | 0 | 69 | 10 | 293 | 303
Total |  |  | 84 | 475 | 12 | 18 | 1 | 36 | 0 | 27 | 2 | 74 | 15 | 155 | 99 | 630 | 729
Grand Total |  |  | 559 |  | 30 |  | 37 |  | 27 |  | 76 |  | 170 |  | 729
BGL |  |  | Cum MARCH-26 |  | 1st April |  | 2nd April |  | 3rd April |  | 4th April |  | Cumulative April'26 |  | Cumulative NGC
GA ID | GA Area | State/UTs | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | Grand total NGC
99.09 | Hyderabad | Telangana | 192 | 261 | 0 | 30 | 0 | 23 | 0 | 39 | 0 | 23 | 0 | 115 | 192 | 376 | 568
1.04 | Kakinada | Andhra Pradesh | 5 | 107 | 0 | 8 | 1 | 8 | 2 | 9 | 2 | 7 | 5 | 32 | 10 | 139 | 149
99.06 | Vijaywada | Andhra Pradesh | 15 | 140 | 0 | 5 | 0 | 7 | 0 | 12 | 0 | 9 | 0 | 33 | 15 | 173 | 188
Total |  |  | 212 | 508 | 0 | 43 | 1 | 38 | 2 | 60 | 2 | 39 | 5 | 180 | 217 | 688 | 905
Grand Total |  |  | 720 |  | 43 |  | 39 |  | 62 |  | 41 |  | 185 |  | 905
Summary |  |  | Cumm MARCH-26 |  | 1st April |  | 2nd April |  | 3rd April |  | 4th April |  | Cummulative April'26 |  | Cummulative NGC
Entity Name |  |  | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified | Old Connection Done & Gasified | Grand total NGC
HPCL |  |  | 2366 | 2022 | 154 | 227 | 229 | 123 | 229 | 115 | 189 | 104 | 801 | 569 | 3167 | 2591 | 5758
HOGPL |  |  | 84 | 475 | 12 | 18 | 1 | 36 | 0 | 27 | 2 | 74 | 15 | 155 | 99 | 630 | 729
BGL |  |  | 212 | 508 | 0 | 43 | 1 | 38 | 2 | 60 | 2 | 39 | 5 | 180 | 217 | 688 | 905
Total |  |  | 2662 | 3005 | 166 | 288 | 231 | 197 | 231 | 202 | 193 | 217 | 821 | 904 | 3483 | 3909 | 7392
Grand Total |  |  | 5667 |  | 454 |  | 428 |  | 433 |  | 410 |  | 1725 |  | 7392

## Sheet1 (hidden)
NGC Progress MIS – Gasified Geographical Area (HPCL & JVs)
HPCL
GA ID | GA Area | State/UTs | April-Feb' 26 Average | Traget(PNGRB) 1st Apr-30th June | Daily New Connection April | Cum. Connection
10.37 | Bareilly, Rampur, Pilibhit | UP | 68 | 200 | 0 | 107
10.47 | Darjeeling, Jalpaiguri & Uttar Dinajpur | WB | 17 | 100 | 0 | 307
10.39 | Etah, Farrukhabad, Hardoi | UP | 25 | 200 | 0 | 122
10.48 | Howrah & Hooghly | WB | 11 | 120 | 0 | 80
10.49 | Nadia & North 24 Parganas | WB | 28 | 120 | 0
10.45 | Shahjahanpur Badaun | UP | 70 | 200 | 0 | 194
9.19 | Sonipat - Jind GA | Haryana | 87 | 150 | 0 | 71
10.43 | Mainpuri Kannauj | UP | 42 | 200 | 0 | 92
10.46 | Nainital Bijnor | UK/UP | 73 | 150 | 0 | 110
10.5 | South 24 Parganas | WB | 5 | 24 | 0 | 21
11.44 | Dausa, Karauli, Sawai Madhopur & Tonk | RJ | 3 | 50 | 0 | 104
Total |  |  | 429 | 1514 | 0 | 1208
Grand Total |  |  | 1943 |  | 0
HOGPL |  |  | Cum MARCH-26 |  | 1st April
GA ID | GA Area | State/UTs | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified
8.03 | Ambala & Kurukshetra Districts | Haryana | 74 | 251 | 12
8.04 | Kolhapur District | Maharashtra | 10 | 224 | 0
Total |  |  | 84 | 475 | 12
Grand Total |  |  | 559 |  | #REF!
BGL |  |  | Cum MARCH-26 |  | 1st April
GA ID | GA Area | State/UTs | New Connection Done & Gasified | Old Connection Done & Gasified | New Connection Done & Gasified
99.09 | Hyderabad | Telangana | 192 | 261 | 0
1.04 | Kakinada | Andhra Pradesh | 5 | 107 | 0
99.06 | Vijaywada | Andhra Pradesh | 15 | 140 | 0
Total |  |  | 212 | 508 | 0
Grand Total |  |  | 720 |  | #REF!

## Sheet2 (hidden)
[7 empty] | NGC | LMC | Reg | CNMD
Gasified Amera | LMC | vendor | team |  | lmc | only ngc 2 nos | 4388 | 5506 | 3779
|  |  |  | 2 | 4

## calculation 30 mar (hidden)
DPNG
GA Name | Cumm. NGC as on 31.12.2025
|  | Jan-Mar | LMC-NGC-Focused | Total
Jind & Sonipat | 4032 | 266 | 52 | 4350
Bareilly, Pilibhit & Rampur | 724 | 496 | 67 | 1287
Farukhabad, Etah, and Hardoi | 840 | 178 | 177 | 1195
Mainpuri & Kannauj | 681 | 516 | 0 | 1197
Nainital & Bijnor | 1430 | 485 | 0 | 1915
Shahjahanpur & Badaun | 2603 | 443 | 306 | 3352
Howrah & Hooghly | 109 | 128 | 397 | 634
Nadia & North 24 Parganas | 256 | 170 | 584 | 1010
South 24 Parganas | 53 | 41 | 0 | 94
Darjilling,Jalpaiguri,Uttar dinajpur | 67 | 627 | 766 | 1460
Dumka,Banka,Godda,Jamtara,Pakur& Sahibganj | 0 | 0 | 0 | 0
Maldah, Birbhum, Murshidabad, Dakshin Dinajpur | 0 | 0 | 0 | 0
Tonk,Sawai Madhopur.Dausa,karauli | 34 | 56 | 0 | 90
Total | 10829 | 3406 | 2349 | 16584

## Revised target (hidden)
S.no | GA ID | Geographical Area/ CGD Networks | State/ Union Territory | Authorized CGD Entity New Name | Date of Authorization | Target completion period (Years) | Date of Target Completion | DPNG Target (Drive) | Connected to Billed | DPNG Registration Target | Commercial Connection Target (Drive) | Reason for change in target
1 | 9.19 | Sonipat District (EAAA) & Jind District | Haryana | Hindustan Petroleum Corporation Limited | 2018-09-26 | 8 | 2028-09-30 | 10000 | 10000 | 10000 | 20 | As Sonipat city is authorized to GAIL Gas, we are left with Jind district and the peripheral areas of Sonipat, which have relatively low potential
2 | 10.37 | Bareilly (EAAA) District, Pilibhit and Rampur Districts | Uttar Pradesh | Hindustan Petroleum Corporation Limited | 2019-03-29 | 8 | 2029-03-31 | 10000 | 10000 | 20000 | 5 | The major potential area of GA 10.37 is Bareilly city, which has been assigned to CUGL.
3 | 10.39 | Farrukhabad, Etah and Hardoi Districts | Uttar Pradesh | Hindustan Petroleum Corporation Limited | 2019-03-29 | 8 | 2029-03-31 | 15000 | 25000 | 30000 | 20
4 | 10.43 | Mainpuri and Kannauj Districts | Uttar Pradesh | Hindustan Petroleum Corporation Limited | 2019-03-29 | 8 | 2029-03-31 | 10000 | 5000 | 20000 | 20
5 | 10.45 | Shahjahanpur and Budaun Districts | Uttar Pradesh | Hindustan Petroleum Corporation Limited | 2019-03-29 | 8 | 2029-03-31 | 15000 | 20000 | 30000 | 5
6 | 10.47 | Darjeeling, Jalpaiguri and Uttar Dinajpur Districts | West Bengal | Hindustan Petroleum Corporation Limited | 29-03-2019 (New start date 01.01.2021) | 10 | 2032-03-31 | 10000 | 15000 | 30000 | 10 | Siliguri is the major business hub and approvals for laying the MDP network are still pending due to the elections, and are expected by 15th May.
7 | 10.48 | Howrah (EAAA) District and Hoogly (EAAA) District | West Bengal | Hindustan Petroleum Corporation Limited | 29-03-2019 (New start date 01.01.2023) | 8 | 2030-12-31 | 10000 | 10000 | 40000 | 10 | The major potential areas of Kolkata town are with Bengal Gas, while the peripheral semi-urban and rural areas with relatively lower potential are with HPCL. Additionally, due to the elections in West Bengal, approval for laying the MDP network has been delayed and is expected by 15th May.
8 | 10.49 | Nadia (EAAA) District and North 24 Parganas (EAAA) District | West Bengal | Hindustan Petroleum Corporation Limited | 29-03-2019 (New start date 01.01.2023) | 8 | 2030-12-31 | 10000 | 10000 | 30000 | 20 | The major potential areas of Kolkata town are with Bengal Gas, while the peripheral semi-urban and rural areas with relatively lower potential are with HPCL. Additionally, due to the elections in West Bengal, approval for laying the MDP network has been delayed and is expected by 15th May.
9 | 10.5 | South 24 Parganas (EAAA) District | West Bengal | Hindustan Petroleum Corporation Limited | 29-03-2019 (New start date 01.01.2022) | 8 | 2030-03-31 | 5000 | 5000 | 10000 | 10 | GA is not yet gasified. The major potential areas of Kolkata town are with Bengal Gas, while the peripheral semi-urban and rural areas with relatively lower potential are with HPCL. Additionally, due to the elections in West Bengal, approval for laying the MDP network has been delayed and is expected by 15th May.
10 | 11.44 | Dausa, Karauli, Sawai Madhopur and Tonk districts | Rajasthan | Hindustan Petroleum Corporation Limited | 2022-03-15 | 8 | 2030-03-31 | 15000 | 7500 | 30000 | 5
11 | 11A.03 | Birbhum, Murshidabad, Maldah & Dakshin Dinajpur districts | West Bengal | Hindustan Petroleum Corporation Limited | 2022-06-17 | 8 | 2030-06-30 | 5000 | 5000 | 30000 | 5 | The GA is yet to be gasified, apart from the WB state election where all approvals of MDP laying has come to halt
12 | 11A.02 | Banka, Dumka, Godda. Jamtara, Pakur & Sahibganj |  |  | 14th- June-22 | 8 |  | 5000 | 5000 | 10000 | 5 | The GA is yet to be gasified, and due to the West Bengal state elections, all approvals for MDP laying have come to a halt.
13 | 10.46 | Nainital Bijnor | West Bengal | Hindustan Petroleum Corporation Limited | 29th- Mar-19 | 8 |  | 10000 | 10000 | 20000 | 5 | The GA is yet to be gasified
Total | [7 empty] | 130000 | 137500 | 310000 | 140

## Govt (hidden)
GA Name | Govt / Institution/PSU/High Rise Name | Household No. | Commercial No. | Consumption (SCM) | Comments
MALDAH GA | BSF(MALDAH) | 500 | 4 | 5100 | MDPE work initiated
MALDAH GA | Railway | 1500 | 0 | 9000 | Agreement executed
NN24 | ISSER | 70 | 1 | 6500 | Area gasified
NN24 | AIIMS | 171 | 6 | 13000 | Agreement executed
NN24 | BSF (Kalyani) | 325 | 5 | 8000 | Proposal submitted to cantonment authorities
NN24 | *Sapoorji Palonji* | 15000 | 0 | 18000 | High-rise development comprising 15,000 households; approval secured for 3,000 households
S24 | IIM (Kolkata) | 75 | 8 | 10000 | Proposal submitted to the college
SB | Rosa Township Reliance(Power plant),Shahjahanpur | 350 | 2 | 8000 | Area gasified
SB | Kribhco Nagar Township,Shahjahanpur | 500 | 1 | 5000 | Agreement executed
SB | Army Cantonment Shahjahanpur | 600 | 4 | 6000 | Approval under process
BRP | CRPF(RAMPUR) | 900 | 5 | 7000 | Concerned authority contacted and approval request letter submitted
BRP | POLITECHNIC COLLEGE- STUDENT MESS | 0 | 2 | 300 | Approval from the college is pending
BRP | IFFCO | 400 | 2 | 8000 | MDPE work in progress
DARJELLING | BSF(SILLIGURI)& (DANI NAGAR) | 1600 | 4 | 9690 | Gasification proposal submitted to cantonment authorities
Mainpuri- Kannauj | Government Colony(Mainpuri) | 600 | 0 | 3600 | Approval received from DM office
Mainpuri- Kannauj | Government Colony(Kannauj) | 200 | 0 | 1200 | Approval received from DM office
Tonk | CSWRI | 300 | 2 | 3600 | Contacted the customer
Tonk | CISF | 250 | 16 | 10000 | Final agreement to be signed.
Tonk | Police line | 300 | 1 | 3500 | The SSP has been contacted for approval.
EFH | Army Cant(Farukhabad) | 1000 | 2 | 8000 | Approval under process

## GSA details (hidden)
Details of GSA s signed after 01.01.2026
Sr no.- | Name of customer | GA Name | GSA type | Estimated consumption in SCMD | Date of GSA | Status ( Started/Not started )
1 | Shree Durga Texcoat Pvt Ltd | JS | Industrial | 300 | 19.03.2026 | Not Started
2 | Anand Knit | JS | Industrial | 500 | 19.03.2026 | Started
3 | Shatabdi Export | JS | Industrial | 1500 | 18.03.2026 | Started
4 | Bansal Processing house | JS | Industrial | 1300 | 19.03.2026 | Started
5 | BCL Fabrics | JS | Industrial | 500 | 18.03.2026 | Started
6 | Shree Karangar Textile Pvt Ltd | JS | Industrial | 200 | 19.03.2026 | Started
7 | Neelam Lace | JS | Industrial | 150 | 08.01.2026 | Started
8 | Ajit Industries 3 | JS | Industrial | 100 | 06.02.2026 | Started
9 | Krishna Polymers | JS | Industrial | 600 | 11.01.2026 | Started
10 | Poddar Tyres and Rubber | JS | Industrial | 200 | 02.01.2026 | Not Started
11 | Vihan Textiles | JS | Industrial | 1300 | 22.03.2026 | Started
12 | Shree Karshni Brass Extrusion | JS | Industrial | 300 | 20.03.2026 | Not Started
13 | A one fibre | JS | Industrial | 400 | 24.03.2026 | Not Started
14 | Twenty first century collection | JS | Industrial | 1200 | 25.03.2026 | Not Started
15 | Navair International | JS | Industrial | 100 | 25.03.2026 | Not Started
16 | Pooja Textiles | JS | Industrial | 300 | 25.03.2026 | Not Started
17 | AS Footcraft | JS | Industrial | 300 | 26.03.2026 | Not Started
18 | Mood Food | BRP | commercial | 41 | 10.03.2026 | Started on 27.03.26
19 | Mama Dhaba | BRP | commercial | 25 | 11.03.2026 | Metering in progress. Not started
20 | Punjabi Rasoi | BRP | commercial | 25 | 11.03.2026 | Not Started
21 | Iffco Mess-1 | BRP | commercial | 50 | 26.01.2026 | Not Started
22 | Iffco Mess-1 | BRP | commercial | 50 | 26.01.2026 | Not Started
23 | Dr Kiran Saujiya CBSE School | MK | Commercial | 70 | 09.03.2026 | Not Started
24 | Dr Kiran Saujiya ISCE School | MK | Commercial | 35 | 09.03.2026 | Not Started
25 | Dr Kiran Saujiya CBSE School (New Mess) | MK | Commercial | 70 | 09.03.2026 | Not Started
26 | Hotel Navratan | MK | Commercial | 25 | 13.03.2026 | Not Started
27 | NMB Sweets and Bakery | MK | Commercial | 20 | 13.03.2026 | Not Started
28 | Sone Raj Hotel | MK | Commercial | 50 | 16.03.2026 | Not Started
29 | Asha Hotel | MK | Commercial | 21 | 18.03.2026 | Not Started
30 | Jagat Aroma | MK | Industrial | 85 | 01.08.25 | Not Started
31 | Suditi Global Academy | MK | Commercial | 30 | 17.09.25 | Started
32 | La Chef | MK | Commercial | 30 | 20.03.25 | Not Started
33 | Aman International | MK | Commercial | 80 | 20.03.25 | Not Started
34 | Asha Hotel | MK | Commercial | 25 | 18.03.2026 | Not Started
35 | Indian Institute of Science and Reasearch( IISER) | NN24 | Commercial | 180 | 09.02.2026 | Supply started on 27.03.26
36 | All Indian Institute of Medical Science (AIIMS), Kalyani – 6 Nos Units | NN24 | Commercial | 330 | 27.03.2026 | Expected to start by 15.05.2026
37 | Monorajan Seva Sadan (Nursing Home) | HH | commercial | 3 | 14.01.2026 | Started
38 | Appayan Lodge (Banquet Hall) | HH | commercial | 3 | 14.01.2026 | Not Started
39 | Shakambari Ispat & Power Ltd | HH | Industrial | 12500 | 10.02.2026 | To be commissioned
40 | Castleton Spring Pvt Ltd | HH | Industrial | 4500 | 13.03.2026 | Factory under Construction
41 | Jaloyog (Sweet Shop) | HH | commercial | 9 | 17.03.2026 | To be commissioned
42 | SAJ Food Products Pvt Ltd (Bisk Farm) | HH | Industrial | 8000 | 25.03.2026 | To be started
43 | Epic Agro Products Pvt. Ltd (Britania Outsourced) | HH | Industrial | 10000 | 25.03.2026 | To be started
44 | Geo Nutri Foods Pvt. Ltd (ITC Outsourced) | HH | Industrial | 5000 | 25.03.2026 | To be started
45 | Aesthetic Nursing Home | HH | Commercial | 60 | 25.03.2026 | To be started
46 | Priti Misthan Bhandar | DJUD | commercial | 15 | 22.01.2026 | Started
47 | Jalpaiguri Govt Engg College | DJUD | commercial | 200 | 22.03.26 | Not started
48 | SAJ Foods Limited | DJUD | Industrial | 20000 | 25.03.26 | Not started - ETC 30.06.26
49 | Vikram Solar | South 24 | Commercial | 50 | 01.01.2026 | Not started
50 | Ghosh Sweets | South 25 | Commercial | 50 | 24.03.2026 | Not started
51 | Websol Energy | South 26 | Commercial | 30 | 27.03.2026 | Not started
52 | Zila Dugdh Utpadak Sahkari Sangh Limited | DKSMT | Industrial | 450 | 23.02.2026 | Not Started
|  |  | Total | 71362

## INDUSCOMMERCIAL (hidden)
Ind/Comm Commissioning
JS | HH | NN24 | DARJELLING | MK | BRP
1.Neelam lace | Shakambari Ispat | IISER:1 | PRITI MISTHAN(MARCH) | SUDITI GLOBAL ACADEMY | MOOD FOOD
2.Ajit industries | Nursing Home. |  | DAS MiSTHAN BHANDAR
3.Krishna polymers |  |  | PAKURTALA MISTHAN BHANDAR
4.Poddar tyres
5.Bcl fabrics
6.Bansal processing house
7.Shatabdi exports
8.Anand knit
9.Vihan textiles
10. Karangar textiles pvt ltd.
SHRI DURGA TEXCOAT
SHRI KARSHNI BRASS EXTRUSION
HSIIDC Foodpark

## target customers (hidden)
SL No | Business / Customer Name | GA Name | District / Location | Expected Commissioning | Expected Volume (SCMD)
1 | Hotel Tara Chicken Corner | BRP | Rampur | 2026-06-01 | 9.88
2 | Karim Chicken Corner | BRP | Rampur | 2026-05-01 | 20.58
3 | Noor-E-Shama | BRP | Rampur | 2026-07-01 | 21.41
4 | Shivam Fast Food | BRP | Rampur | 2026-05-01 | 12.35
5 | Kesar Food | BRP | Rampur | 2026-06-01 | 24.7
6 | Manthan Restaurant | BRP | Rampur | 2026-06-01 | 23
7 | Food Plaza | BRP | Rampur | 2026-07-01 | 9.88
8 | Dosa Darbar | BRP | Rampur | 2026-07-01 | 16.47
9 | Biggies Pizza | BRP | Rampur | 2026-08-01 | 37.05
10 | Hungry Point | BRP | Rampur | 2026-08-01 | 16.47
11 | Opal restaurant | BRP | Rampur | April'26 | 50
12 | Radiance hotel | BRP | Rampur | May'26 | 40
13 | Punjabi Tadka | BRP | Rampur | 2026-07-01 | 24.7
14 | Delhi-6-Zaika | BRP | Rampur | 2026-08-01 | 24.7
15 | Hotel Delite | BRP | Rampur | 2026-09-01 | 14.82
16 | Bombay Hotel | BRP | Rampur | 2026-09-01 | 42.81
17 | Hotel Krishna | BRP | Rampur | 2026-09-01 | 13.17
18 | Karims Food | BRP | Rampur | 2026-09-01 | 39.52
19 | Batra Restaurant | BRP | Rampur | 2026-10-01 | 21.41
20 | Zaika Darbar | BRP | Rampur | 2026-10-01 | 34.58
21 | Dominos | BRP | Rampur | 2026-10-01 | 27.99
22 | Chicken King | BRP | Rampur | 2026-12-01 | 45.5
23 | The Olive & Cheese | BRP | Rampur | 2026-12-01 | 36.4
24 | Al-Baike Restaurant | BRP | Rampur | 2026-12-01 | 36.4
25 | IFFCO Township Mess (2 Nos) | BRP | Aonla | 2026-06-01 | 50
26 | Maheshwari Restaurant | BRP | Aonla | 2027-01-01 | 19.5
27 | Kwality Restaurant | BRP | Aonla | 2026-12-01 | 27.3
28 | Om Sai Restaurant | BRP | Aonla | 2026-12-01 | 18.2
29 | Family Restaurant | BRP | Aonla | 2027-01-01 | 18.2
30 | Raj Dhaba | BRP | Aonla | 2026-12-01 | 36.4
31 | Shiva Dhaba | BRP | Aonla | 2026-12-01 | 27.3
32 | Rajasthani Dhaba | BRP | Aonla | 2026-12-01 | 24.7
33 | Shivam Dhaba | BRP | Aonla | 2026-12-01 | 18.2
34 | Mustakim | BRP | Aonla | 2026-08-01 | 26
35 | New Bharat Dhaba | BRP | Aonla | 2026-08-01 | 13
36 | Great Indian Rasoi | BRP | Pilibhit | 2026-07-01 | 33.8
37 | Everyday Pizza Pilibhit | BRP | Pilibhit | 2026-06-01 | 15.6
38 | Yaara Da Adda | BRP | Pilibhit | 2026-06-01 | 39
39 | Fitness Food Arena | BRP | Pilibhit | 2026-08-01 | 13
40 | Max Pizza | BRP | Pilibhit | 2026-09-01 | 10.4
41 | Delhi Darbar | BRP | Pilibhit | 2026-10-01 | 24.7
42 | Delhi Darbar Hotel | BRP | Pilibhit | 2027-01-01 | 10
43 | Utsav Green Hotel & Restaurant | BRP | Pilibhit | 2027-01-01 | 13
44 | Pawan Sweets | BRP | Pilibhit | May'26 | 50
45 | Hotel Solitaire | BRP | Pilibhit | May'26 | 50
46 | Sino India | JS | Sonipat | 2026-05-01 | 4000
47 | Shellz India | JS | Sonipat | 2026-05-01 | 1200
48 | Fine Foods India | JS | Sonipat | June'26 | 100
49 | Polyplast India | JS | Sonipat | June'26 | 200
50 | HSIIDC Mega Food Park | JS | Sonipat | Mar'26 | 150
51 | Chicken Processing Plant | NN24 | Nadia | 2026-09-01 | 9000
52 | Chicken Rendering Plant | NN24 | Nadia | 2026-09-01 | 600
53 | IISER | NN24 | Nadia | 2026-03-01 | 175
54 | BSF | NN24 | Nadia | 2026-06-01 | 200
55 | AIIMS | NN24 | Nadia | 2026-05-01 | 430
56 | 10 Commercial Customers (Paharpur) | Darjeeling GA | Jalpaiguri | 2026-03-01 | 400
57 | Pakurtala Mistanna Bhandar, Kartik Sweets, Lords Confectionery, Biryani House, Priti Mistanna Bhandar, Hazi Biryani, BB Biryani, Roy Hotel, Pritam Hotel, Montu Miro | Darjeeling GA | Jalpaiguri | 2026-03-01 | 200
58 | Kanki Dham | Darjeeling GA | Kanki, Uttar Dinajpur | 2026-06-01 | 70
59 | Switz Foods | Darjeeling GA | Jalpaiguri | 2026-05-01 | 400
60 | Tirupati Fence | Darjeeling GA | Jalpaiguri | 2026-09-01 | 1000
61 | Bisk Farm | Darjeeling GA | Darjeeling | 2026-09-01 | 15000
62 | Royal Castle | NB | Bijnor | 2026-07-01 | 12.6
63 | Nandi Sweet | NB | Bijnor | 2026-07-01 | 75.4
64 | Gappu Gol | NB | Bijnor | 2026-07-01 | 31.4
65 | Bakey Bihari Restaurant | NB | Bijnor | 2026-10-01 | 37.7
66 | Pankaj Hotel | NB | Bijnor | 2026-11-01 | 25.1
67 | Kathi Corner | NB | Bijnor | 2027-01-01 | 10
68 | Avyan Restaurant | NB | Bijnor | 2027-01-01 | 19.6
69 | Gazal Restaurant & Bar | NB | Nainital | 2026-11-01 | 324
70 | Hotel Sangat Prime | NB | Nainital | 2026-11-01 | 162
71 | Kumaoni Rasoi | NB | Nainital | 2026-11-01 | 108
72 | Hidden Leaf Cafe & Resto | NB | Nainital | 2026-11-01 | 108
73 | The Klay | NB | Nainital | 2026-12-01 | 216
74 | Chocolate Factory | NB | Nainital | 2026-12-01 | 54
75 | Hotel Amardeep | NB | Nainital | 2026-12-01 | 405
76 | Reliance Awadh Canteen | SB | Shahjahanpur | 2026-03-01 | 9
77 | Reliance TH Canteen | SB | Shahjahanpur | 2026-03-01 | 30
78 | Reliance VIP Guest House | SB | Shahjahanpur | 2026-03-01 | 6
79 | Pizza 99 | SB | Shahjahanpur | 2026-05-01 | 6
80 | Royal Panna | SB | Shahjahanpur | 2026-05-01 | 95
81 | Krishna Lawn & RK Resort | SB | BD | 2026-06-01 | 4
82 | Swaruchi Food Garage | SB | BD | 2026-06-01 | 9
83 | Rajmahal | SB | BD | 2026-09-01 | 14
84 | Pari Namkeen | SB | Shahjahanpur | Negotiations underway | 400
85 | NMB Bakery | MK | Mainpuri | 2026-04-01 | 25
86 | Brijwasi Sweets | MK | Mainpuri | 2026-05-01 | 80
87 | Gauri Sugandh | MK | Kannauj | 2026-06-01 | 550
88 | Hotel Shubhadra | MK | Kannauj | 2026-06-01 | 16
89 | Super Aroma | MK | Kannauj | 2026-07-01 | 360
90 | Hotel Asha | MK | Kannauj | 2026-06-01 | 80
91 | Hotel M L Palace | MK | Kannauj | 2026-08-01 | 16
92 | Kiran Saujiya | MK | Mainpuri | 2026-05-01 | 105
93 | Hotel Rajdhani | MK | Mainpuri | 2026-11-01 | 55
94 | TP Garden & Hotel | MK | Mainpuri | 2027-01-01 | 140
95 | Hotel Raj Regency | MK | Mainpuri | 2027-01-01 | 25
96 | Himadri Speciality Chemicals Ltd | HH | Singur | 2026-11-01 | 50000
97 | Exceltric Industries Pvt Ltd | HH | Howrah | 2026-12-01 | 4500
98 | Skipper Ltd (Unit-Uluberia) | HH | Howrah | 2027-02-01 | 30000
99 | Skipper Ltd (Unit-Jalan) | HH | Howrah | 2027-02-01 | 30000
100 | Ceratizit India Pvt Ltd | HH | Howrah | 2027-03-01 | 2000
101 | Bisk Farm | HH | Howrah | 2027-03-01 | 3500
102 | Hindustan Colas Uluberia | HH | Howrah | 2027-03-01 | 4000
103 | Nezone Steels (WB) LLP | HH | Hooghly | 2027-03-01 | 10000
104 | Jindal (India) Ltd | HH | Howrah | 2027-03-01 | 6000
105 | ITC Food | EFH | Sandila Industrial Area (Ph-2), Hardoi | Sep' 26 | 6000
106 | Bala Ji Wafers Ltd | EFH | Sandila Industrial Area (Ph-2), Hardoi | Dec' 26 | 2000
107 | Proficienty Management | EFH | Sandila Industrial Area (Ph-2), Hardoi | Jun' 26 | 1200
108 | SP Metal | EFH | Sandila Industrial Area (Ph-2), Hardoi | Jun' 26 | 250
109 | Berger Paints india Ltd | EFH | Sandila Industrial Area (Ph-1), Hardoi | Dec' 26 | 1000
110 | Garg Saltpeter Industries | EFH | Sasni Road Jalesar | May' 26 | 650
111 | Garg Trading Company | EFH | Sasni Road Jalesar | May' 26 | 650
112 | Baba Tarders | EFH | Dargah Road Jalesar | May' 26 | 650
113 | Shubham Nitro Chem | EFH | Station Road Jalesar | Apr' 26 | 650
114 | Savitri Traders | EFH | Station Road Jalesar | May' 26 | 650
115 | Capital Saltpetre Works | EFH | Sadabad Road jalesar | May' 26 | 650
116 | Mor Mukut and Sons | EFH | Sadabad Road jalesar | May' 26 | 650
117 | Subhash Trading Company | EFH | Sadabad Road jalesar | May' 26 | 650
118 | Srinivas and Sons | EFH | Begumpur Jalesar | Apr' 26 | 650
119 | Kamlesh Enterprises | EFH | Samaspur Road Jalesar | Apr' 26 | 650
120 | Basant lal MORMUKUT | EFH | Sadabad Road jalesar | May' 26 | 650
121 | Agarwal Saltpiter Industry | EFH | Bypass road Jalesar | Apr' 26 | 650
122 | Yogesh Agarwal and Company | EFH | Sadabad Road jalesar | May' 26 | 650
123 | Agarwal Enterprises | EFH | Bypass road Jalesar | May' 26 | 550
124 | Pranav Industries | EFH | Jalesar Market | May' 26 | 120
125 | Mohd Yaseen Saltpeter | EFH | Dargah Road Jalesar | May' 26 | 200
126 | SK Traders | EFH | Sadabad Road jalesar | May' 26 | 550
127 | Shri Bhagwati Saltpetre and Chloride Works | EFH | Bypass road Jalesar | May' 26 | 550
128 | Muhammad Ismail Kha Salpeter Works | EFH | Sadabad Road jalesar | May' 26 | 550
129 | Radha Krishna Faquir Chandra | EFH | Bypass road Jalesar | May' 26 | 250
130 | RS Saltpeter | EFH | Sadabad Road jalesar | May' 26 | 550
131 | Bishamver Nath and Sons | EFH | Bypass road Jalesar | May' 26 | 550
132 | Rashi Enterprises | EFH | Sadabad Road jalesar | Jun' 26 | 550
133 | Umsani Salpeter | EFH | Bypass road Jalesar | Jun' 26 | 550
134 | SS Saltpeter | EFH | Jalesar Market | Jun' 26 | 550
135 | NKH Salepeter | EFH | Dargah Road Jalesar | Jun' 26 | 550
136 | Prabha Enterprises | EFH | Dargah Road Jalesar | Jun' 26 | 200
137 | Nida Saltpeter | EFH | Dargah Road Jalesar | Jul' 26 | 200
138 | Indra Deo and Sons | EFH | Dargah Road Jalesar | Jul' 26 | 200
139 | Anjani Enterprises | EFH | Sadabad Road jalesar | Jul' 26 | 200
140 | Bhavuk Bansal SO Vinod Bansal | EFH | Bypass road Jalesar | Jul' 26 | 20
141 | Shivek Metals | EFH | Sadabad Road jalesar | Jul' 26 | 20
142 | Arts Impex | EFH | Bypass road Jalesar | Aug' 26 | 20
143 | Shri Balaji Trading Co | EFH | Dargah Road Jalesar | Aug' 26 | 20
144 | Prabha restarant & Hotel | EFH | Etah | 2026-06-01 | 33.4963
145 | Priya restaurant & Hotel | EFH | Etah | 2026-06-01 | 33.4963
146 | shubham sweets | EFH | Etah | 2026-06-01 | 25.1222
147 | Gnga sweets | EFH | Etah | 2026-07-01 | 20.9352
148 | casa royale hotel | EFH | Etah | 2026-08-01 | 20.9352
149 | Devshagar restaurant | EFH | Etah | 2026-08-01 | 20.9352
150 | Silver Plate Resturant | EFH | Farrukhabad | 2026-05-01 | 3.9667
151 | Lucky Caters And Resturant | EFH | Farrukhabad | 2026-05-01 | 7.9333
152 | Puse Lal Sweets | EFH | Farrukhabad | 2026-06-01 | 7.9333
153 | Neelkanth Sweets | EFH | Farrukhabad | 2026-06-01 | 89.9111
154 | Tirupati Restaurant | EFH | Hardoi | 2026-06-01 | 50.2444
155 | ATITHI HOTEL & RESTAURANT | EFH | Hardoi | 2026-07-01 | 25.1222
156 | Pooja Hotel | EFH | Hardoi | 2026-03-01 | 30.4111
157 | Hotel Basant Leela | EFH | Hardoi | 2026-09-01 | 37.0222
158 | H K Hotel & Lawns | EFH | Hardoi | 2026-03-01 | 50.2444
159 | Siddhartha Palace Hotel | EFH | Hardoi | 2026-04-01 | 31.7333
160 | Spice & Flavour Restauran | EFH | Hardoi | 2026-08-01 | 19.8333
161 | Sammi halwai | EFH | Hardoi | 2026-06-01 | 125.6111
162 | Rajwada restaurant | EFH | Hardoi | 2026-06-01 | 25.1222
163 | Treat garden restaurant | EFH | Hardoi | 2026-08-01 | 16.7481
164 | Mircharam Sweets | EFH | Hardoi | 2026-06-01 | 50.2444
165 | Awadh restaurant | EFH | Hardoi | 2026-06-01 | 16.7481
166 | Gokul Hotel | RJ GA | Tonk | 2026-04-01 | 600
167 | Rashtriya Sweets | RJ GA | Tonk | 2026-06-01 | 1200
168 | Royal Orchid | RJ GA | Tonk | 2026-06-01 | 1000
169 | CSWIR | RJ GA | Tonk | 2026-09-01 | 750
170 | CISF Deoli | RJ GA | Tonk | 2026-09-01 | 23250
171 | Rama Resort | RJ GA | Tonk | 2026-09-01 | 4500
172 | Kanak Family Dhaba | RJ GA | Tonk | 2026-11-01 | 600
173 | Shakuntalam | RJ GA | Tonk | 2026-11-01 | 1000
174 | Shyam Leela Bakery | RJ GA | Tonk | 2026-12-01 | 600
175 | Raj Palace | RJ GA | Tonk | 2026-12-01 | 750
176 | Prakash Café | RJ GA | Tonk | 2026-12-01 | 600
177 | M/s Almatis Alumina | S24 | S24 | 2026-12-01 | 8000
178 | Crypton Industries | S24 | S24 | 2026-08-01 | 1000
179 | M/s Cheviot | S24 | S24 | 2026-09-01 | 1200
180 | M/s Cresmac | S24 | S24 | 2026-11-01 | 1000
181 | Himadri Speciality Chemicals Ltd | S24 | S24 | 2027-02-01 | 1000